## Sheet1
Section | Task | Hours | Cost
Store Builder Admin Interface
Front-end development | Stores
| Create, edit or remove a store | 6 | 900
| Restore a backup of an existing store | 3 | 450
Landing pages
| Add a section | 1 | 150
Add a content block to a section
| Page header (title and description) | 1 | 150
| Category tiles (title, description, image, link and button text) | 5 | 750
| Link to a category using a search option of category data added | 4 | 600
| Link to an external URL (e.g. search results page) | 1 | 150
| Banners (image(s) and link) | 2 | 300
| YouTube videos (title and link) | 2 | 300
| Plain text | 2 | 300
| Plain HTML (html editor) | 3 | 450
| Carousels (images(s) and links) | 4 | 600
| Rich Relevance (specify category name / id) | 2 | 300
| Change the order of a section or content block | 2 | 300
| Change the size of a content block (full-, half- and one-third-widths) | 1 | 150
| Remove a section or content block | 2 | 300
Category and product data
| Add category (name) | 3 | 450
| Rich Relevance flag (on / off) to display recommendations for category | 2 | 300
| Add a subcategory (name, description, feature image, list of skus) | 10 | 1500
| Rich Relevance flag (on / off) to display recommendations for given subcategory | 2 | 300
| Change the order of a category or subcategory | 2 | 300
| Remove a category or subcategory | 2 | 300
Back-end development | Save and publish
| Save changes |  | 0
| Automatically publish all changes to test environment | 5 | 750
| Any unsaved changes will be lost if user closes their browser | 2 | 300
| Discard changes |  | 0
| Cancels all local changes made during a browser session | 3 | 450
| Publish changes to production environment |  | 0
| Time and date-stamped backup created before changes are pushed to production | 3 | 450
Services
| Create service to store and retrieve store data | 5 | 750
| Create service to authenticate user | 5 | 750
Backups
| Retain backups of each store for up to 30 days | 1 | 150
Integration and training | Deploy application | 2 | 300
| Test full integration | 2 | 300
| Training for full use of admin interface | 1 | 150
Totals |  | 91 | 13650
Single Page Store Application
Front-end development | Retrieve store data from back-end service | 8
| Provide routes to load specific content (e.g. link to a specific category or sub-category) | 6 | 900
| Responsive UI | 16 | 2400
| Category tiles, banners, videos, etc respond to screen sizes | 8 | 1200
| Category tile navigation becomes a slider at certain screen sizes | 8 | 1200
| Product grid behaves as per production product list | 2 | 300
| Test on all major supported browsers | 8 | 1200
| Product display |  | 0
| Connect to new product, availability and price services in FRA | 16 | 2400
| Utilize product grid components from FRA | 8 | 1200
| Rich Relevance products displayed | 8 | 1200
Back-end development | Content loading of landing page and assets (images, CSS, etc.) into CMS (Joomla) | 3 | 450
| Creation of article and menu items in Test CMS with preview link | 1
| Creation of article and menu items in Production CMS with preview link | 1
Total |  | 93 | 12450
Grand Total |  | 184 | 27600